## Sheet1
| IAC Internship Program 2023 - Machine Learning Development Log |  |  |  | Project Name - EduPredict: Graduation & Placement Prediction
Project Manager - Harshada Topale
Intern ID - 4024
Sr | Problem Statement | Task | Details | Date | Status | Comments
1 | Year Of Graduation Prediction
1.1 |  | Data Preprocessing | Imported necessary libraries, loaded the dataset, handled missing values, and performed data cleaning. | 2024-07-28 | Completed | Data is clean and ready for analysis.
1.2 |  | Feature Engineering | Created new features based on the existing data to improve model accuracy. | 2024-07-28 | Completed | New features added successfully.
1.3 |  | Model Selection | Evaluated various machine learning models (e.g., Linear Regression, Decision Trees) to select the best performing one. | 2024-07-28 | Completed | Decision Tree model selected for further development.
1.4 |  | Model Training | Trained the Decision Tree model on the training dataset. | 2024-07-28 | Completed | Model trained with 95% accuracy on training data.
1.5 |  | Model Evaluation | Evaluated the model performance using testing data and various metrics (e.g., RMSE, MAE). | 2024-07-28 | Completed | Model evaluation shows 90% accuracy on test data.
1.6 |  | Hyperparameter Tuning | Optimized the model parameters to improve performance. | 2024-07-29 | Completed | Hyperparameters tuned for optimal performance.
2 | Placement Status Prediction
2.1 |  | Data Preprocessing | Imported necessary libraries, loaded the dataset, handled missing values, and performed data cleaning specific to placement data. | 2024-07-29 | Completed | Data is clean and ready for analysis.
2.2 |  | Feature Engineering | Created new features such as extracurricular activities, internships, and CGPA. | 2024-07-29 | Completed | New features added successfully.
2.3 |  | Data Splitting | Split the dataset into training and testing sets. | 2024-07-29 | Completed | Data split into training (75%) and testing (25%).
2.4 |  | Model Selection | Evaluated various machine learning models (e.g., Logistic Regression, Random Forest) to select the best performing one. | 2024-07-29 | Completed | Random Forest model selected for further development.
2.5 |  | Model Training | Trained the Random Forest model on the training dataset. | 2024-07-30 | Completed | Model trained with 93% accuracy on training data.
2.6 |  | Model Evaluation | Evaluated the model performance using testing data and various metrics (e.g., Precision, Recall). | 2024-07-30 | Completed | Model evaluation shows 88% accuracy on test data.
2.7 |  | Hyperparameter Tuning | Optimized the model parameters to improve performance. | 2024-07-30 | Completed | Hyperparameters tuned for optimal performance.