## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | EduPredict: Graduation & Placement Prediction |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | Atharv Musale (Intern ID -4024)
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2024-07-28 | Encountered issues with integrating and testing the data processing and model training modules. | Development | No | Implement continuous integration and testing during the development phase. Ensure modular development to facilitate easier integration and testing. | Adopted continuous integration practices and performed regular testing of individual modules. Ensured the development process was modular to allow for easier integration. | Developer | Solved | Continuous integration and modular development are essential practices to ensure smooth development progress.
2 | 2024-07-27 | During the initial data preparation phase, we encountered inconsistencies in the dataset, such as missing values and duplicate entries. | Data Quality | Yes | Implement a robust data validation and cleaning process at the start of the project. Use automated scripts to identify and handle missing values, duplicates, and other data quality issues. | Developed and applied data cleaning scripts using Python libraries (Pandas and NumPy) to preprocess the dataset. Ensured all missing values were appropriately handled and duplicates were removed. | Developer | Solved | Regular data quality checks should be integrated into the workflow to maintain the integrity of the data throughout the project lifecycle.
3 | 2024-07-29 | Testing phase revealed lower than expected model accuracy and performance issues. | Testing | No | Allocate sufficient time for testing and validation. Use diverse test datasets to uncover potential issues and refine models accordingly. | Extended the testing phase and used a variety of test datasets to validate model performance. Iteratively refined the model based on test results. | Developer | Solved | Thorough testing with diverse datasets is crucial to ensure the robustness and accuracy of machine learning models.
4 | 2024-07-30 | Deployment phase faced unexpected compatibility issues with existing systems. | Deployment | No | Conduct deployment testing in a staging environment that mimics the production setup. Collaborate closely with the IT team to address compatibility issues. | Set up a staging environment for deployment testing. Worked closely with the IT team to resolve compatibility issues and ensure smooth deployment. | Developer | Solved | Testing deployment in a staging environment helps identify and resolve compatibility issues before going live.
5 | 2024-07-31 | Closure phase highlighted gaps in the documentation of processes and lessons learned. | Closure | No | Maintain detailed documentation throughout the project lifecycle. Regularly update documents to reflect changes and lessons learned. | Developed a comprehensive documentation process to be maintained throughout the project. Ensured all team members contributed to the documentation of lessons learned. | Developer | Solved | Consistent documentation throughout the project ensures all processes and lessons learned are recorded accurately for future reference.