## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | EduPredict: Graduation & Placement Prediction |  | Project Id: | 4024 | Project Manager: | Harshada Topale |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 1 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2024-08-03 | Project Team Lead: | Sarang Kadakia |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 5 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Insufficient data quality | Model accuracy may be affected | Model accuracy may be affected | Data Scientist | Critical |  | Closed | Risk
2 | Risk | Technical issues with model deployment | Delays in project delivery | Have a backup plan and perform regular testing during development | Developer | High |  | Closed | Assumption
3 | Assumption | Availability of historical student data | Project can proceed as planned | Confirm data availability before project initiation | Data Scientist | Moderate |  | Closed | Issue
4 | Issue | Inaccurate predictions in initial models | May affect stakeholders' trust in the system | Continuously refine models and validate with new data | Data Scientist | High |  | Closed | Dependency
5 | Dependency | Reliance on third-party tools for data processing | Project may be delayed if tools are unavailable | Identify alternative tools and plan for contingencies | Developer | Low |  | Closed
6 | [8 empty] | Open
Closed
Critical
High
Moderate
Low
Negligible