## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
| IAC Internship Program 2023 - Machine Learning Project Schedule |  |  |  |  | Project Name - EduPredict: Graduation & Placement Prediction
Project Manager - Harshada Topale
| PROJECT START DATE | 2024-07-24 |  |  |  | Project End Date - 03-Aug-2024
Overall Progress - Completed
Sr No | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments
1 | Requirements Gathering
1.1 |  | Identify necessary data and project scope |  |  | Data Analyst | 2024-07-24 | 2024-07-25 | 2024-07-25 | 3Hrs | Completed | 100 | Data collection completed successfully and project scope defined.
1.1.1 |  |  | Collected data from various sources | Data sources | [5 empty] | Completed
1.1.2 |  |  | Defined project objectives and deliverables | - | [5 empty] | Completed
1.1.3 |  |  | Conducted stakeholder interviews | - | [5 empty] | Completed
1.1.4 |  |  | Analyzed existing data systems | - | [5 empty] | Completed
1.1.5 |  |  | Created initial project requirements document | - | [5 empty] | Completed
2 | Project Planning
2.1 |  | Develop a project plan |  |  | Project Developer | 2024-07-25 | 2024-07-26 | 2024-07-26 | 2.5Hrs | Completed | 100 | Project plan developed with detailed tasks, timelines, and resource allocation.
2.1.1 |  |  | Outline tasks and timelines | - | [5 empty] | Completed
2.1.2 |  |  | Allocate resources | - | [5 empty] | Completed
2.1.3 |  |  | Identify project milestones | - | [5 empty] | Completed
2.1.4 |  |  | Develop risk management plan | - | [5 empty] | Completed
3 | Project Design
3.1 |  | Design data pipeline and machine learning models |  | Data schema | Project Developer | 2024-07-26 | 2024-07-27 | 2024-07-27 | 3Hrs | Completed | 100 | Design phase completed with all necessary architectural and model designs.
3.1.1 |  |  | Create data pipeline architecture | - | [5 empty] | Completed
3.1.2 |  |  | Develop model design | - | [5 empty] | Completed
3.1.3 |  |  | Select appropriate machine learning algorithms | - | [5 empty] | Completed
3.1.4 |  |  | Design data preprocessing steps | - | [5 empty] | Completed
3.1.5 |  |  | Create data validation strategy | - | [5 empty] | Completed
4 | Project Development
4.1 |  | Implement data processing, model training, and evaluation |  | Development tools, Data quality | Project Developer | 2024-07-27 | 2024-07-29 | 2024-07-30 | 7Hrs | Completed | 100 | Data processing, model training, and evaluation implemented successfully.
4.1.1 |  |  | Develop data processing scripts | - | [5 empty] | Completed
4.1.2 |  |  | Train machine learning models | - | [5 empty] | Completed
4.1.3 |  |  | Evaluate model performance | - | [5 empty] | Completed
4.1.4 |  |  | Optimize model parameters | - | [5 empty] | Completed
5 | Testing
5.1 |  | Validate model accuracy and performance using test data |  | Test data | Data Scientist | 2024-07-30 | 2024-07-29 | 2024-07-31 | 3Hrs | Completed | 100 | Model accuracy and performance validated successfully with test data.
5.1.1 |  |  | Prepare test datasets | - | [5 empty] | Completed
5.1.2 |  |  | Run tests on models | - | [5 empty] | Completed
5.1.3 |  |  | Analyze test results | - | [5 empty] | Completed
5.1.4 |  |  | Document any issues found | - | [5 empty] | Completed
5.1.5 |  |  | Implement necessary fixes and retest | - | [5 empty] | Completed
6 | Deployment
6.1 |  | Deploy models and generate predictions for practical use |  | - | Data Scientist | 2024-07-31 | 2024-07-30 | 2024-08-01 | 3Hrs | Completed | 100 | Models deployed successfully and predictions generated for practical use.
6.1.1 |  |  | Set up deployment environment | - | [5 empty] | Completed
6.1.2 |  |  | Deploy trained models | - | [5 empty] | Completed
6.1.3 |  |  | Monitor deployment for any issues | - | [5 empty] | Completed
6.1.4 |  |  | Generate initial predictions | - | [5 empty] | Completed
6.1.5 |  |  | Validate deployment success | - | [5 empty] | Completed
7 | Closure
7.1 |  | Document the process, results, and lessons learned |  | - | Project Developer | 2024-08-01 | 2024-08-03 | 2024-08-03 | 5Hrs | Completed | 100 | Project documentation compiled and project closure report completed.
7.1.1 |  |  | Compile project documentation | - | [5 empty] | Completed
7.1.2 |  |  | Document lessons learned | - | [5 empty] | Completed
7.1.3 |  |  | Archive project materials | - | [5 empty] | Completed
7.1.4 |  |  | Finalize project closure report | - | [5 empty] | Completed
Note on G7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you